## Login Page
Bug Report - Login Page
No | Title | Bug Description | Steps to Reproduce | Expected Result | Actual result | Priority | Severity | Screenshots | Status | Remark
1 | Cross button on the 'Error! Invalid Credentials' error is not responding | Cross button on the 'Error! Invalid Credentials' error is not responding | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter invalid username and invalid password. 3.Click on sign in button | Error should disappear when clicked on the cross button | Error does not disappear when clicked on the cross button | Medium | Low |  | DONE
2 | Eye button to view password doesnot disappear | Eye button to view password doesnot disappear when clicked on enter button instead of sign in button | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter invalid username and invalid password. 3.Click on Enter button | Eye button to view password should disappear | Eye button to view password doesnot disappear | Medium | Low |  | DONE
3 | copy and paste username and password in the fields is allowed | We are able to copy and paste user name and password in the fields and login successfully | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.copy and paste valid user name and password in the fields 3.Click on Enter button | copy and paste user name and password in the fields should not be allowed | copy and paste user name and password in the fields is allowed | High | Low |  | DONE
4 | Log out button is not working | Log out button not working from the left side bar column | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter valid username and valid password. 3.Click on Logout button from the home page in the left column | Alert message should pop up and if clicked on yes then user should be logged out | Log out button not working | High | Low |  | DONE
5 | Change password functionality not working | Change password functionality not working | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter valid username and valid password. 3.Click on the logo in the top right corner and click on Change password option | Change password functionality should work | Change password functionality not working | High | Low
6 | Same error shown when field kept blank | No specific error when username field is kept blank as 'Enter Username' | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.keep username field blank and enter valid password. 3.Click on Enter button | There should be specific error when username field is kept blank as 'Enter Username' | No specific error when username field is kept blank as 'Enter Username' | Medium | Low |  | DONE
7 | Same error shown when field kept blank | No specific error when password field is kept blank as 'Enter Password' | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.enter valid username field blank and keep password field blank. 3.Click on Enter button | There should be specific error when Password field is kept blank as 'Enter Password' | No specific error when Password field is kept blank as 'Enter Password' | Medium | Low |  | DONE
8 | Same error shown when field kept blank | No specific error when both password field and username field is kept blank | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.keep both username and keep password field blank. 3.Click on Enter button | There should be specific error when both username and keep password field kept blank as 'Enter Username and Password' | No specific error when username and Password field are kept blank as 'Enter Username and Password' | Medium | Low |  | DONE
9 | Manage account functionality not working | Manage account functionality not working | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter valid username and valid password. 3.Click on the logo in the top right corner and click on Manage account option | Manage account functionality should work | Manage account functionality not working | High | Low |  | DONE
10 | Same error shown when field is entered incorrect data | No specific error when username field is entered with incorrect data as 'incorrect Username' | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter incorrect username and valid password. 3.Click on Enter button | There should be specific error when username field is entered with incorrect data as 'incorrect Username' | No specific error when username field is entered with incorrect data as 'incorrect Username' | Medium | Low |  | PRIVACY POLICY
11 | Same error shown when field is entered incorrect data | No specific error when Password field is entered with incorrect data as 'incorrect Password' | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter incorrect username and valid password. 3.Click on Enter button | There should be specific error when Password field is entered with incorrect data as 'incorrect Password' | No specific error when Password field is entered with incorrect data as 'incorrect Password' |  |  |  | PRIVACY POLICY
12 | Fields do not get highlighted for invalid input | Username field doesnot get highlighted for invalid input or blank input | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter incorrect username or blank username 3.Click on Enter button | Fields should get highlighted for invalid input | Fields do not get highlighted for invalid input | Medium | Low |  | NA
13 | Fields do not get highlighted for invalid input | Password field doesnot get highlighted for invalid or blank input | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user 2.Enter incorrect password or blank password 3.Click on Enter button | Fields should get highlighted for invalid input | Fields do not get highlighted for invalid input | Medium | Low |  | NA
14 | Welcome' text above the username field on the login page is not in centre | Welcome' text above the username field is not in centre | 1.Open the URL https://dev-portal.svkm.ac.in/researches/user | Welcome' text above the username field on the login page should be in centre | Welcome' text above the username field on the login page is not in centre | Medium | Low |  | DONE
15 | Error message for invalid credentils should be proper and well structured | Invalid error message is displaying not properly and not easy for user as well as it should be in proper modal |  | Invalid credentials message should display in proper format or user friendly | invalid credentials message is occuring on top of the page and not proper design and not easy to read and check | High | low |  | NA